MedBook

Software Development Plan

Version 1.1

Revision History

| **Date** | **Version** | **Description** | **Author** |
| --- | --- | --- | --- |
| 29/10/21 | 1.0 | Complete section 1, 2, 3, 4.1, 4.2, 4.3.1, 4.3.3 | NPVy, NNDu, NKTTNga |
| 12/11/21 | 1.1 | Complete section 4.3.2 | NNDu |
|  |  |  |  |
|  |  |  |  |

Table of Contents

[**Introduction**](#_heading=h.30j0zll) **[4](#_heading=h.30j0zll)**

[**Project Overview**](#_heading=h.1fob9te) **[4](#_heading=h.1fob9te)**

[*Project Purpose, Scope, and Objectives*](#_heading=h.3znysh7) *[4](#_heading=h.3znysh7)*

[*Assumptions and Constraints*](#_heading=h.2et92p0) *[4](#_heading=h.2et92p0)*

[*Project Deliverables*](#_heading=h.tyjcwt) *[4](#_heading=h.tyjcwt)*

[**Project Organization**](#_heading=h.3dy6vkm) **[4](#_heading=h.3dy6vkm)**

[*Organizational Structure*](#_heading=h.1t3h5sf) *[4](#_heading=h.1t3h5sf)*

[*Roles and Responsibilities*](#_heading=h.4d34og8) *[4](#_heading=h.4d34og8)*

[**Management Process**](#_heading=h.2s8eyo1) **[5](#_heading=h.2s8eyo1)**

[*Project Estimates*](#_heading=h.17dp8vu) *[5](#_heading=h.17dp8vu)*

[*Project Plan*](#_heading=h.3rdcrjn) *[5](#_heading=h.3rdcrjn)*

[Phase and Iteration Plan](#_heading=h.26in1rg) [5](#_heading=h.26in1rg)

[Releases](#_heading=h.lnxbz9) [5](#_heading=h.lnxbz9)

[Project Schedule](#_heading=h.35nkun2) [6](#_heading=h.35nkun2)

[*Project Monitoring and Control*](#_heading=h.1ksv4uv) *[8](#_heading=h.1ksv4uv)*

[Reporting](#_heading=h.44sinio) [8](#_heading=h.44sinio)

[Risk Management](#_heading=h.2jxsxqh) [8](#_heading=h.2jxsxqh)

[Configuration Management](#_heading=h.z337ya) 8

Software Development Plan

# Introduction

This Software Development Plan will define the development activities for developing the MedBook App. Every detail of the development, test and deployment process will be covered in this document.

# Project Overview

## Project Purpose, Scope, and Objectives

Purpose: The primary goal of this project is to create an application that helps people to make an appointment with their doctors along with some convenient features.

Scope: This project is meant to reach out to everyone and every class of society.

Objectives: Create a fully functional application for making appointments and checking health for patients and doctors.

## Assumptions and Constraints

* The project has a fixed schedule of 10 weeks.
* Zero-budget project.
* The project has 5 people, there will be no more people added during the project.
* Android test only.


## Project Deliverables

Deliverables of the project are identified in the project schedule. Deliverables include:

* Vision Document
* Software Development Plan
* Software Architecture Document
* Test cases and reports
* Weekly Report
* Source code

# Project Organization

## Organizational Structure

**

## Roles and Responsibilities

| ***Person*** | ***Role*** |
| --- | --- |
| **Hồ Ngọc Minh Đức**  **Ngô Phú Chiến**  **Nguyễn Phương Vy**  **Ngô Nhật Du**  **Nguyễn Kim Thị Tố Nga** | *Project manager*  *Developer*  *Database designer*  *UI designer*  *Tester* |

# Management Process

## Project Estimates

Project Time: 10 weeks ( 5 sprints)

Members: 5 people

## Project Plan

### Phase and Iteration Plan

| **Phase** | **Iterative** | **Objectives** | **Milestones** |
| --- | --- | --- | --- |
| Inception | Sprint 1 | Define the scope of project, business use-case, product requirements. Draw up the project plan and make a description of the project goal, risks, and business model. | Scope and business case agreement |
| Elaboration | Sprint 2 | Analysis, design use-case models, and specify the structure of each model. | Use-case model |
| Sprint 3 | Complete use-case specification and establish product prototype architecture. | Baselined architectural prototype. |
| Construction | Sprint 4 | Revise Software Architecture.  Design UI for the software system, implement and test M1 version. | M1 version |
| Sprint 5 | Fixing the previous version and complete implementation.  Test plan and test case. | M2 version |

### Releases

**M1 (MedBook version 1)** contains most of basic functions as below:

* Admin’s features
* Sign in and Sign up
* Set up/Manage appointment schedule
* Review appointment history and medical information
* Searching hospital’s and doctor’s information
* Notification

**M2 (MedBook version 2)** should have these features including:

* Discount
* Pay for treatment
* Human Resources Management


Some additional features may be implemented like:


* Update medical news
* Private Chat
* Donation


***Time releases:***

* M1: 11/12/2021
* M2: 25/12/2021

### Project Schedule

**

**

**

## Project Monitoring and Control

### Reporting

Weekly meeting via Zoom every Tuesday and every other Friday.

Weekly status report on Google Drive: update at every meeting.

Informal chats via Facebook Messenger group chat.

### Risk Management

| ***Risk ID*** | ***Risk Description*** | ***Probability*** | ***Impact*** | ***Priority*** | ***Mitigation Strategy or Contingency Plan*** |
| --- | --- | --- | --- | --- | --- |
| 1 | Software technical problem | 6/10 | 9/10 | High | - Punctuated software updates in order to fix the situation. |
| 2 | Data loss | 5/10 | 8/10 | High | - Inform other members, relocate the lost information.  - Reupdate information to the software. |
| 3 | Low performance | 3/10 | 5/10 | High | - Accelerate and optimize performance, especially in the designing and analyzing phase. |
| 4 | Information leakage | 3/10 | 7/10 | Medium | - Enhance privacy security. |
| 5 | Overdue deadlines | 2/10 | 6/10 | Medium | - Prioritize punctuation to meet the deadlines’ requirements on time and not to affect other members’ schedules. |

### Configuration Management

Google Drive for storing and shuttering documents and files.

GitHub for managing code and related files.